## Sheet1
Task | Duration | Start Date | End Date | Dependencies
Planning and Design | 1 week | 2023-11-28 | 2023-12-04
- Define Requirements | 5 days | 2023-11-28 | 2023-12-02
- Design UI/UX | 3 weeks | 2023-12-05 | 2023-12-25 | Define Requirements
Frontend Development | 1 week | 2023-12-26 | 2024-01-01 | Design UI/UX
- Implement Landing Page | 5 days | 2023-12-26 | 2023-12-30
- Customer Login Form | 3 days | 2024-01-02 | 2024-01-04
- Repair Center Login Form | 3 days | 2024-01-02 | 2024-01-04
Backend Development | 2 weeks | 2024-01-05 | 2024-01-18 | Implement Landing Page
- Set Up Server | 1 week | 2024-01-05 | 2024-01-11
- Implement APIs | 1-2 weeks | 2024-01-12 | 2024-01-25 | Set Up Server
Database Setup | 2 weeks | 2024-01-26 | 2024-02-08 | Create Customer Table
- Create Customer Table |  | 2024-01-26 | 2024-02-08
- Create Repair Center Table |  | 2024-02-09 | 2024-02-22 | Create Customer Table
Integration and Testing | 1 week | 2024-02-23 | 2024-03-01 | Implement APIs
- Test Frontend and Backend | 2 weeks | 2024-03-02 | 2024-03-15 | Integration and Testing
- Integration Testing | 2 weeks | 2024-03-16 | 2024-03-29 | Test Frontend and Backend
Deployment | 1-2 weeks | 2024-03-30 | 2024-04-12 | Integration Testing
- Deploy to Production | 1-2 weeks | 2024-04-13 | 2024-04-26 | Deployment
Documentation | 1 week | 2024-04-27 | 2024-05-03 | Deploy to Production
- Write Project Documentation |  | 2024-04-27 | 2024-05-03